## Air
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Air Management
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
Definition of emergency/emergency engine |  | Merrily Gere | 2019-09-24 | Approved with technical corrections
Adopt a Permit by Rule to replace the General Permit to Limit Potential to Emit Permits (new RCSA sections 22a-174-33a and -33b) |  | Raquel Herrera | 2020-06-01 | Public comment period closed 11/22/19
New Source Review permitting Program, amends 22a-174-1-3 |  | Paula Gomez | Spring 2020 | Pub HRG 1/29, Comments due 1/31
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Exemptions from New Source Review permitting for certain small incinerators |  | Stationary Source Control Group | Summer 2020 | Internal agency review ongoing
Update of source monitoring requirements |  | Stationary Source Control Group | Fall 2020 | Internal agency review ongoing
Modernization of radiation regulations |  | Radiation Division | Fall 2020 | Internal agency review ongoing

## WPLR
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Water Protection & Land Reuse
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRCHearing Date | Status
Remediation Standard Regulations 22a-133k1-3 |  | Kevin Neary | Winter 2020 | Comment period closed 11/12.
Environmental Use Regulations |  | Amy Richardson | Summer 2020 | Comment period closed 11/12.
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Water Quality Regs: 22a-426-1 through -9 |  | Water Planning & Management Division | Winter 2021 | Internal agency review ongoing

## BETP
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Energy & Technology Policy
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
New HFC Regulations |  | Bureau of Energy & Technology Policy | Summer 2020 | Informal review OTG & OPM
Pursuant to PA 19-35 -Update to the High Performance Building Regulations (CGS §16a-38k) |  | Office of Demand | Spring 2020 | Internal agency review ongoing

## Natural Resources
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Natural Resources
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
State-controlled Wildlife Management Areas 23-5c-1 et seq. and New 26-55-7. |  | Robin Blum | 2020-01-28 | Pending review LRRC
Pursuant to P.A. 19-28, creating a cooperative multi-state possession/landing program for the Winter 1 commercial summer flounder fishery 26-159a-29. |  | Justin Davis | 2019-12-18 | Final as of 12/23/2019
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Work cooperatively with NY to adopt regulations for the whelk fishery in Long Island Sound. |  | Fisheries Division | 2020-04-01 | Internal agency review ongoing
Per direction from Atlantic States Marine Fisheries Commission, adopt new regulations for horseshoe crab fishery to reduce harvest. |  | Fisheries Division | 2020-03-01 | Internal agency review ongoing
Per direction from Atlantic States Marine Fisheries Commission, implement a mandatory tagging program for commercial tautog fishery. |  | Fisheries Division | 2020-04-01 | Internal agency review ongoing
New regulations establishing a fee to reinstate an expired forest practitioner certification (23-65h-1), and require use of BMPs to protect water quality during timber harvests 23-65j-1. |  | Division of Forestry | Summer 2020 | Requires adoption of proposed amendments to the Forest Practices Act
Endangered species list- revise list of endangered and threatened species, and species of special concern. |  | Division of Wildlife | Fall 2021 | Internal agency review ongoing
Clarify hunting in proximity to buildings occupied by person or domestic animals or used for storage of flammable or combustible materials, or shooting towards persons Section 26-67c. |  | Division of Wildlife | Fall 2021 | Internal agency review ongoing
Update regulations concerning mooring of boats at state boat access areas Section 26-112-39 |  | Fisheries Division | Spring 2020 | Internal review ongoing
Update bow & arrow fishing regs and makes clarifying change to creel limit definition Section 26-112-43. |  | Fisheries Division | Spring 2020 | Internal agency review ongoing
Remove Black Pond (Woodstock) and Mohawk Pond from the list of lakes & ponds with a closed season from the last day of February to Opening Day. To conform with other proposed changes (see section 26-112-46(d.) |  | Fisheries Division | Spring 2020 | Internal agency review ongoing
Revision to: 1) Carp regs as per legislative intent (to provide additional opportunities for bow fishers).Section 26-112-45 2) add Tiger Muskie with Northern Pike for methods and limits (creel, length), 3) add Crescent Lake to the list of lakes & ponds with a 3 catfish per day creel limit. |  | Fisheries Division | Spring 2020 | Internal agency review ongoing
Update and make clarfications to Special Management Areas Section 26-112-46 . 1) Add Black Pond (Woodstock) and Mohawk Pond to the list of Trout Management Lakes, 2) establishes “thermal” refuges on highland Lake, 3) Under subsection (h). Amends designation from Atlantic Salmon Broodstock Areas to “Atlantic Salmon Management Areas” better reflect current management goals, 4) revises subsection to provide additional opportunities for bow fisher, 5) provides exception to allow temporary retention of carp for measuring. |  | Fisheries Division | Spring 2020 | Internal agency review ongoing
Repeal Sections 26-112-24 (Closed seasons) and 26-112-47 (State-controlled fishing areas). Sec. 26-112-24: Eliminates outdated provisions concerning a statewide closed season. Sec. 26-112-47: Eliminates outdated provisions concerning the now defunct Quinebaug Valley Trout Hatchery Public fishing Ponds. |  | Fisheries Division | Spring 2020 | Internal agency review ongoing

## BMMCA
Predictable Regulation (Goal 15) Project Tracking
Division | Bureau of Materials Management & Compliance Assurance
Beyond Public Notice
Anticipated Regulatory Adoption/Amendment |  | Point of Contact | LRRC Hearing Date | Status
Pre-Public Notice
Regulatory Concepts under Consideration |  | Point of Contact | Goal for Public Notice | Status
Underground Storage Tanks Regulaiton update |  | Emergency Response and Spill Prevention Division | Fall 2020 | Need EPA review Internal agency review ongoing
Hazardous Waste regulation update |  | Engineering & Enforcement Division | Fall 2020 | Need EPA review Internal agency review ongoing
Spill Reporting update |  | Emergency Response and Spill Prevention Division | Fall 2020 | Internal agency review ongoing