## Sheet1
| Revision Date: | 2014-10-10 | Author: | Mary Baier | Phone No.: | (860) 594-3256
Prepared by:
Comments
Drawings
Are the drawings stamped by a Professional Engineer Licensed in the State of CT?
The Contractor's proposal must meet all requirements established in regulatory permits for the Project and must also conform to the requirements of Section 1.10.
Can the operations take place with in a reasonable time frame, in accordance with any limits of operations set forth in the contract, Permit Requirements, or the Contractor's Schedule?
Do the interior dimensions offer enough room to perform the work as planned?
Can all designated stages of work be performed in proposed sheeting locations, or will they have to be adjusted?
Placement and/or storage of excavated material addressed?
Does the bottom elevation of the cofferdam clear any battered piles?
Are the construction equipment locations depicted?
Are sumps shown for dewatering?
Does the placement of the sumps avoid pulling water through the work area?
Working drawings should indicate type of connections and member shapes.
Is there an installation and/or removal sequence suggested?
Is there sufficient overhead clearance to perform installation and removal?
Are temporary support conditions clear, such as bolted and welded connections, etc?
Drawings should specify elevations for water, freeboard, and maximum excavation depth. They should be 2' more than bottom of granular fill or excavation as indicated on the plans.
If a tremie or cofferdam seal is called for on the plans, does the working drawings address this issue?
If a tremie or cofferdam seal is called for on the plans, does the working drawings address this issue?
Cofferdam Next to Railroad
Latest crane inspection included?
Are the applicable safety factors included?
Can the installation anticipated take place within the appropriate time frame for track and/or electrical outages? If not, has or will the RR give permission for extended construction?
Grounding of work zone indicated on working drawings?
Cofferdam Next to Navigable Waterways
Configuration of the barges included, loading sequence, stability provisions, if applicable?
Anticipated locating of barge during installation sequence included?
Are tide elevations indicated? Freeboard?
Are there plans for collision protection? (i.e. Dolphin structures)
Ice dam information and prevention procedures?
Other agency approvals required? DEP, USCG, USCORPs, etc.
Cofferdam Next to Buildings
Is a pre-survey of the building(s) necessary? Masonry Structure?
If dewatering will be taking place has potential settlement of the building been considered?
Has the effect on surrounding structures due to vibrations during installation been taken into account?
Calculations
Does the plan contain design calculation for all temporary and construction loads?
Calculations should include structural adequacy and stability for water and soil loading.
Is contractor owned material is it consistent with the working drawings?
Pre-engineered devices such as clamps, manufacturers certification or catalog cuts are adequate.
Contrary to popular belief these systems do not have to abide by AASHTO guidelines as they are temporary structures.
Is there provision for incidental impact on compression struts?
Do the calculations contain a check of soil stability against piping and/or heave?
If Contractor owned material is used, is it the correct grade of steel?
Coordination
Should this working drawing make reference to other contract documents? (i.e., HASP, LHPP, etc.)
Do other agencies have to review and comment on the plan (Railroad, USCG, DEP,harbor master, Designer,Soils and Foundations, etc.)
Should a meeting take place with all stakeholders?
Field Inspection
Does the material for construction match the working drawings?
Cofferdams that have become tilted or misplaced prior to completion shall be righted prior to work.
Was the water level inside the cofferdam maintained at the same level at the outside water level while placing the foundation seal?
Was the concrete sealed cofferdam dewatered after the concrete strength was sufficient to withstand the hydrostatic pressure?
Are all interlocking connections oriented correctly? Many types of sheeting connections are required to be oriented a specific way.
All excavated material shall be kept 2' from edge of cofferdam unless indicated on the working drawings.
Tie-back bolts are not to be used to pull sheeting flush with the wales. Separate bolts are to be used for this.
Footings placed on bedrock should have the bottom cut to the specific elevation: level, stepped or serrated, foundation surfaces cleaned and all seams and crevices grouted.
If footings placed on an excavated surface other than bedrock, was the bottom undisturbed and compacted prior to forming?
Backfilling should take place in 6" lifts unless otherwise indicated by the plan or the Engineer.
Cofferdam removal shall be inaccordance with the working drawings.
All material shall be removed. Any material that can not be removed shall be submitted in writing with the reason for being left in place.
In tidal waters, ice should not be allowed to form within 3' of the cofferdam.
Does the sheet piling wall extend high enough to stop moving boulders or soil from entering the excavation?
Ice is a problem in any water that can change elevations, not only tidal waters.