## Complete Projs
| Revision Date: | 2012-09-28 | Author: | Michael Strong | Phone No.: | (860) 594-3306
Prepared by:
Comments
Heading
Step 1A: Contractor - Complete Contract work.
Step 1B: Contractor - Finalize test reports (mechanical, electrical, tank monitoring, fire alarm - including NFPA form, etc.) required for issuance of the Certificate of Compliance. Refer to individual Contract specifications.
Step 1C: Contractor - Start assembly of Operation & Maintenance Manual.
Step 1D: Contractor - Develop an outline training schedule (with no dates) to organize it fo the owner. Contractor should include Contract listed number of hours where stated as a guideline to develop. Submit to DOT.
Step 2: DOT - Review outline schedule and identify what training shall be performed prior to building occupancy. Schedule with Contractor.
Step 3A: Contractor - Complete training required prior to occupancy using draft unsubmitted Operation & Maintenance Manual.
Step 3B: Contractor - Submit Preliminary Air and Water Balance Report to Designer.
Step 4: DOT - Designer reviews and submits comments; can proceed to Steps 5 and 6 concurrently if determined feasible by Designer.
Step 5: Contractor - Submit Final Air and Water Balance Report to Designer.
Step 6: Hold Semi-Final Inspection - Refer to Form 816 Article 1.20-1.08.12 for prerequisites.
Step 7: Contractor - Submit warranties to Designer. Complete Final Inspection prerequisites, refer to Form 816 Article 1.20-1.08.12 for complete list. Partial list includes the following: submission of closeout documents and asbestos -free certification, deliver spare parts to Engineer, complete training using draft Operation & Maintenance Manual, begin demobilization. This step may be done concurrent with Step 5.
Step 8: Contractor - Punch-list work (typically this takes about 1 week).
Step 9: DOT - Occupy facility if Certificate of Compliance can be issued at this time and Step 7 is complete.
Step 10: Hold Final Inspection.
Step 11: DOT - Occupy facility once Certificate of Compliance issued ( if not done at Step 9).
Step 12: DOT - Designer reviews and submits comments on closeout documents.
Step 13: Contractor - Resubmit closeout documents.