## Drainage
| Revision Date: |  |  | 2011-03-03 | Author: | Michael Washington | Phone No.: | (860) 823-3105
Prepared by:
Comments
Culvert Pipe Installation
Review plans and specifications for culvert installation.
Verify if pipe to be used is the proper size, type, and sufficient length.
Verify if proper joint sealing/connection material is on site.
Verify if correct bedding material on site and free of large stones and debris.
Verify the drainage components have been tested and approved.
Visually check pipes for damage (unacceptable cracks, broken collar, damaged coatings, etc.).
Is cast date on units?
Was the material shipped earlier than allowed by specification?
If concrete pipe was shipped early, was it approved by the Engineer?
Were cylinder break results for the concrete pipe provided?
Has asphalt coated pipe coating thickness been checked by district lab personnel?
Verify if trench is in correct location.
Is trench safe for inspection?
Check trench for proper width, depth, and sheeting needs and record depth.
Check bed for proper grade and compaction; check bedding shape.
Verify bell end of pipe is upstream of flow.
Ensure pipes fit snugly together and there is no debris in the pipe.
Track number of pipe sections installed to verify quantity placed.
Verify if backfill placed in proper lifts or as allowed by the Engineer.
Verify if there is sufficient cover material over the pipe to allow construction vehicles to cross.
Verify if proper warning tape is installed, which should be green.
Catch Basin Installation
Review plans and specifications for catch basin installation.
Verify proper location for catch basins.
Verify basin size/sump is correct for precast/block basins and if the wall thickness is correct.
Verify proper top curb style and if it matches curbing.
Verify material has been tested, including cast dates, blocks/bricks, sand, cement, water, etc.
Ensure proper compaction and bedding material used.
Is basin in rock cut?
Is basin in wet area requiring use of stone?
Verify if weep holes are installed.
If precast unit has multiple knock-outs, has unused knock-outs been "bricked/blocked" closed?
Ensure interior of basin has been parged where needed.
Ensure no overhanging of basin top. If so, ensure the exterior is parge to eliminate it.
Verify proper throat opening for future cleaning.