## Drilled Shaft
| Revision Date: | 2011-03-03 | Author: | John Dunham | Phone No.: | (203) 785-8082
Prepared by:
Comments
Contractor and Equipment Arrive On Site
Has the contractor submitted a Drilled Shaft Installation Plan?
Has the Drilled Shaft Installation Plan been approved?
Does the Contractor have an approved Concrete Mix Design (Concrete Placement?)
The equipment being used is consistent with the Drilled Shaft Installation Plan
Has the contractor run the required Trail Mix and slump loss test for their concrete mix design(Concrete Placement)?
Has the Contractor performed a satisfactory slump loss test incase there is a concreting delay?
If the Contractor proposed a blended mineral-polymer or polymer slurry, do they have an approved Slurry Management Plan?
Is the Contractor prepared to take soil samples or rock cores on the bottom of the shaft in accordance with xxx.35.5, Exploration (Shaft Excavation)?
Has the site preparation been completed for footing in accordance with Construction Sequence?
Does the Contractor have all the equipment and tools shown in the Drilled Shaft Installation Plan?
If casing is to be used, is it the right size in accordance with specifications?
If the Contractor plans to use a manufactured slurry, do they have the proper equipment to mix it?
Is a desander required for Slurry?
If a desander is required, does the Contractor have it on site and operational?
Does the Contractor have the required equipment to perform tremie ?
Trial Shaft
Is the trial shaft positioned away from the production shafts or as specified in the contract documents (xxx.31 Trial Shaft Installation)?
Has the Contractor performed a successful test hole in accordance with Trial Shaft Installation?
Did the Contractor cut off the shaft below grade in accordance with Trial Shaft Installation?
Has the Contractor revised the technique and equipment to (and the revision approved) to successfully construct a shaft?
Shaft Excavation and Cleaning
Is the shaft being constructed in the correct location and within tolerance?
Does the Contractor have a benchmark so the shaft can be constructed and inspected to the proper elevations?
Did the contractor record overburden depth and rock socket depth?
If the shaft has a rock socket, did we confirm top of competent rock?
If the shaft has a rock socket, is the bottom clean?
If the Contractor is using slurry, can they perform tests and report results in accordance with specifications for Slurry?
Is the slurry level being properly maintained in accordance with Slurry plan?
Are you filling out the Soil and Rock Excavation forms?
The discharge end of the tremire pipe was maintained in the concrete with the proper head above it
Are the proper number and types of tests being performed on the slurry in accordance with the specifications?
If permanent casing is being used, does it meet specifications (tested)?
If temporary casing is being used, does it meet specifications?
Is the Contractor maintaining an excavation log?
Is the shaft within allowable vertical alignment tolerances?
Is the shaft of proper depth?
Comments
Reinforcing Cage
Is the rebar the correct sizes and configured in accordance with the project plans?
Is the rebar properly tied in accordance with specifications?
Does the Contractor have the proper spacers for the steel cage in accordance with the specifications?
Does the Contractor have the proper amount of spacers for the steel cage in accordance with the specifications?
If the steel cage was spliced, was it done in accordance with contract documents?
Is the steel cage secured from settling and from floating (during concrete placement steel cages sometimes rise with the placement of the concrete)?
Is the top of the steel cage at the proper elevation?
Has testing tubes been installed if required?
Concreting Operations
Prior to concrete placement, has the slurry (both manufactured and natural) been tested in accordance with contract specifications?
If required, was the casing removed in accordance with specifications?
Was the discharge end of the tremie maintained in the concrete mass with proper concrete head above it?
If free-fall placement (dry shaft construction only), was concrete place in accordance with specifications?
Did concrete placement occur within the specified time limit?
Were concrete acceptance tests performed as required?
When placing concrete, did the Contractor overflow the shaft until good concrete flowed?
Post Installation
If shaft is constructed in open water, is the shaft protected until the concrete reaches the required compressive strength?
Is all casing removed to the proper elevation for using Permanent Casing?
If required, has the Contractor complied with Nondestructive Evaluation?
Is the shaft within the applicable construction tolerances?
Have you documented the pay items?
Notes/Comments