## Material Stored
|  | Revision Date: | 2014-09-22 | Author: | Christopher Angelotti | Phone No.: | (860) 594-2672
Prepared by:
Comments
Prior to utilizing this checklist it is recommended that you review Section 1-909 of the Construction manual and Article 1.09.06-B of the Standard Specifications.
Material Stored in State:
Contractor Responsibilities:
Letter requesting payment for material stored received.
The schedule of values is submitted with adequate detail.
The certificate of title (or receipted bill- see the Construction manual for info) is completely filled out all accompanying documentation is received and no wording has been changed.
The necessary testing has been submitted.
District Responsibilities for material stored in State.
Testing approved by DMT
District estimate of the unit costs of the item agree with the Contractor submitted schedule of values and ADE approval generated.
If two above are not true a reduced payment amount has been agreed upon (See Construction Manual).
Once the schedule of values is evaluated and seems reasonable inspect the storage location for conformance and inventory the material.
If the inventory cannot be matched to the requested payment the request must be revised by the Contractor.
All necessary documents are included in the Volume 4. (Certificate of title; schedule of values and ADE acceptance, inspection and inventory requirements).
Unit for material stored determined and discussed with Project Engineer.
Material Stored out of State:
Contractor Responsibilities:
Letter requesting payment for material stored received.
The schedule of values is submitted with adequate detail.
Material list is supplied with correlation to marking on stored material.
The certificate of title (or receipted bill- see the Construction manual for info) is completely filled out, all accompanying documentation is received and no wording has been changed.
The necessary testing has been submitted.
District Responsibilities for material Stored out of State
Develop an estimate of the unit costs of the item which the Contractor is requesting material stored on site.
Compare the Contractor submitted schedule of prices to the District estimate for the costs of the item (See the construction manual for details). Transmit letter to Contractor accepting schedule of values. This to be included in package to OOC.
Determine whether the initial and quarterly inventories will require extra costs to the Department and if so the ADE to discuss with OOC prior to proceeding.
ADE Correspondence to DMT requesting inspection and inventory of material and supplying material list.
Confirm that all necessary documentation is received from the Contractor in accordance with Section 1-909 of the construction manual.
Forward a copy of the Contractor’s request with all necessary documentation and the District’s recommendation for approval or denial of the Schedule of values to the Construction Division Chief.
Upon receiving the approval or denial of the request for material stored payments back from the Construction Division Chief with the Necessary documentation of testing, storage site inspection and material inventory the District is to determine the unit for material stored as outlined above.
Inspection for Both In-State or Out-of-State Material Storage:
The storage site and material must be personally inspected and the material inventoried to make sure the site is secure and the material inventory matches the certificate of title.
Initial and quarterly inventories are to be performed by designated personnel depending upon the storage location.
Along with the inventory, the Department representative must note if there is any visible damage to the material.
Damaged materials shall be brought to the attention of the Division of Material Testing and shall not be paid as material stored. If the material was paid prior to identifying that it was damaged a deduction from the next payment estimate must be made.