## Movable Bridge
| Revision Date: | 2014-08-27 | Author: | Anthony Kwentoh | Phone No.: | (860) 594-2673
Prepared by:
Comments
Types of Movable Bridges
The bridges have various Mechanical, Electrical and Structural components. This checklist is predominantly based on Bascule bridges.
Bascule bridges (Single or Double Leafs)
Vertical lift bridges
Horizontal Swing Bridges (Center or Rim bearing)
Construction Monitoring
Review the project plans and special provisions for details and scope of work required for rehabilitation or reconstruction of any movable bridge.
Familiarize with the staging plans and contractor's work scheme, which includes use of barges and work platforms.
Review and monitor the Contractor's fall protection safety plans.
Familiarize with the contract M&PT plan and TMP.
Monitor traffic impacts daily and make adjustments as directed by engineer.
Marine traffic must be maintained per contract provisions.
Comply with U.S. Coast guard permit requirements and notification process.
Communicate to nearby businesses and community prior to lane closures.
Consider the safety of the traveling public, pedestrians and construction workers to be of utmost importance.
Prior to staged deck removal, verify that protection barriers (TPCBC's and Guiderail system) separating work area from traffic are properly installed.
Monitor movable span balancing schemes during stage construction.
Any standing water in the counterweight pits should be removed.
A detour plan using approved route should be in-place per contract plans.
Environmental Monitoring
Is the bridge over navigable watercourse? Enforce permit requirements.
What is the possibility of contractor's accidental spill into the watercourse?
Are containment measures in place? Verify that work plan will prevent construction debris from falling into the watercourse.
Verify that oil absorbent booms are installed per contract plans or permits.
Check to ensure contractor provides adequate spill kits at bridge site.
E&S controls must be installed per plans.
Lead paint removal process and field painting work must adhere to the environmental regulations, sensitivity to watercourse and community.
Monitor contractor's compliance with permit conditions, Fed and State regulations. All work must be done within allowable time-of-year restrictions.
Construction Schedules and Tracking Submittals
Review contractor's schedules (baseline and updates) to verify work activities progress, and assess deviations. Request recovery schedule when delays are noted to get back on track.
Monitor long lead items closely in correlation to the scheduled milestones.
Track submittals status, procurement of materials and delivery.
Verify that the Contractor's shop drawings have been reviewed and stamped approved.
Working drawings have been reviewed and concurred by the engineer.
Ensure that all catalog cuts submitted have been reviewed and stamped approved by the engineer.
Ensure that all material furnished conform to the contract documents or as approved by the engineer.
General Structure | [5 empty] | Comments
Following contract plan details for repairs, inspect concrete surfaces for areas of deterioration and extent of crack repairs, patching and full replacement.
Verify that the fabricated structural steel members meet the plan dimensions and configuration for proper fit.
Ascertain that all steel components are fabricated with raw stock produced in USA, as listed in the material certifications on all federally funded projects.
Bolted Structural Steel Connections
Verify that all bolts for structural members meet specifications.
Ensure that temporary bolts are replaced with permanent bolts in any steel connection.
Verify that bolts are tightened to the specified torque per plan.
Inspector must witness the final tightening of all bolts in a connection, using calibrated wrench tightening or the turn-of-nut tightening.
Coordination with the Rocky Hill lab on steel member testing or welding card inspection/testing.
Field Welded Structural Steel Connections
Refer to the Standard Specifications Form 816, Section 6.03 for welded structural steel connections, which shall meet the requirements of AASHTO/ANSI/AWS D1.5 Bridge welding codes.
Ensure that all field welding of new steel members to existing steelwork complies with the contract plan details and specifications, approved shop and working drawings.
Check the contract documents to verify required field tests on field welded connections, such as magnetic particle and ultrasonic exams.
Movable Bridge Deck
Know the required scope of work for rehabilitation or replacement of the steel grid deck, which may be open grid or filled with concrete.
Verify that the steel grid deck panels are fabricated per the approved shop drawings prior to installation.
Check the grid bars for deterioration and broken welds.
Bridge Field Alignment and Balancing
Due to shifts in the weight distribution after deck repairs or replacement, the movable bridge will need to be rebalanced for proper operation.
Check for differential movement of the bridge leafs under live traffic.
Check span locks for wearing of surface and binding against the socket.
Check balance calculations for center of gravity errors. Balance adjustments done by modifying the counterweights.
Contractor will perform detailed calculations to account for the new weight of the moving span leafs in reference to both horizontal and vertical axes.
Bascule and Vertical lift bridges, strain gauge analysis will be performed to determine the imbalance condition of the movable span leafs for the existing and the completed bridge rehabilitation.
Dynamic strain gauges will be attached to the machine span drive shafts connecting the primary and secondary speed reducers to record the imbalance data.
Positive imbalance (+) indicates span heavy condition. Balancing will involve adding more counterweights.
Negative imbalance (-) indicates counterweight heavy condition. Balancing will require removing some counterweight blocks.
The span leaf will be in balance if the center of gravity is either directly above or below the Trunnion. It is not desirable for the center of gravity of the bridge to coincide perfectly with the center of rotation at the trunion. Span should stay closed under traffic with its own weight.
Bascule bridge should be slightly toe heavy (10,000 to 15,000 foot-pound from the trunion). Vertical Lift bridge should be slightly span heavy. Movable span should not bounce under live load.
The movable bridge balance changes during the opening and closing cycles as the center of gravity rotates about the Trunnion. Imbalance should not overload the machinery and / or electrical units.
Movable bridge is required to be properly balanced for all angles of operation, to prevent over work of the operating systems.
Check the alignment of the pinion shafts relative to each other before matching and assembling the bascule bridge structural steel girder webs, etc.
Contractor balancing procedure must address step-by-step sequence for each stage of the work.
Verify that total weight of movable bridge span remains within the safe operating limits of the bridge operating systems.
Verify that the submittal for contractor balancing procedure is approved prior to modifying the counterweights. Concrete and or steel dimensions must be as shown in the balance calculations.
Span Locks
Verify the span locks secure the movable leafs in closed position to align and lock the bridge from horizontal and vertical displacements under live traffic loads.
The span lock assembly may need to be repaired or replace worn parts under the project scope due to heavy wear from operation.
Functional test done to verify that the contractor operate each lock with hand crank or manual pump.
Check clearances of the lock bar to the receiver to prevent rubbing or binding. Replace lock bar socket parts that are severely worn out.
Verify span lock sockets have machined surfaces.
Trunnion Assemblies
Verify the scope of work, and shop drawing details required to rehabilitate the assemblies, consisting of trunnion, trunnion hub, hub rings, alignment plugs, trunnion bearings, trunnion bearing pedestals, fasteners and misc. hardware.
Traffic Gates and Navigation Lights
Verify functional tests performed for proper operation of traffic gates for opening and closing time. Time not to exceed 15 seconds in either direction per U.S. Coast Guard requirements.
Verify proper operation of channel navigation lights (Red to Green).
Check that all lights work properly on backup battery by simulating outage to allow passage of marine vessels.
Bridge Electrical Systems
Ensure all electrical work meets NEC codes and AASHTO standards.
Verify functional tests performed for rehabilitated electric motor and hydraulic drive produces continuous speed to open and close bridge.
Verify that the backup generator functions to deliver full power if primary electric power is out.
Check wire circuits are labeled and wiring is neat and easy to follow.
Incorporate wiring changes to the electrical and control system As-Builts.
Verify that the Automatic Transfer Switch during loss of power will transfer power source to generator, and return to normal power with minimal time delay upon transfer, not to exceed 15 seconds.
Bridge Machinery Systems
The mechanical components varies- Motor, Drive Speed Reducers, Drive Shafts, Pinion, Trunnion, Bearings, Brake system, Lock Bars, Sheave Track and Rack System, Balance Wheels, Hydraulic pumps and cylinders, etc.
Get familiar with machinery and control systems problems and determine which party is responsible (Contractor or State) is responsible under the contract.
Ensure all moving parts and gear - teeth, shaft bearings are cleaned and lubricated as specified in the bridge operations and maintenance manual.
Verify that defective parts are replaced or repaired per contract plans.
Set the brakes (motor and machinery) with enough torque so they can stall out the motor. Verify that wind forces will not overpower the brakes when motor cuts off.
Field test to ensure the brakes are set based on the factory specified spring deflection.
Align rack and pinion gear teeth to within 0.005" .
Proper alignment of shaft couplers and gear backlash.
Drill permanent mounting holes for machinery after coupler alignment is confirmed to be within tolerance.
Check sump pump and sump pit to ensure floats don't hang up on the sump walls
Bridge Control Systems
Relay-based system or Programmable logic controller (PLC) system are types of control systems used to operate movable bridges from the control desk.
Functional tests must be performed to demonstrate that the bridge properly operates, all safety features work correctly, and out of sequences operation are preventable.
Check emergency stop of the movable span during opening and closing phases, at full speed, and at creep speed.
Test all remote limit switches to simulate faults for span locks, gates, navigation lights, etc.
Check all manual override selections at the control desk to verify proper bridge operations.
Disconnect electric power source and verify that the automatic transfer switch (ATS) activates the backup generator within 15 seconds.
ATS should return back to electric power when line is switched.
Verify that new control systems matches the existing and the approved cat. Cut / shop drawing.
Substructure Protection Systems
Circular Cells of steel sheeting or Timber piles Fender protection systems are used to protect the substructures from aberrant vessel collision with a bridge.
Verify required repairs to the fender systems as detailed in the contract plans and specs.
Underwater inspections and repairs may be necessary to restore the integrity of the protection system.
Movable Span Trial Openings
Vessel passage process using permissive interlocks and traffic safety devices. The control desk position indicator lights are used to guide the operations.
Operator sounds a horn, and activates traffic signals to RED.
All clear signal using Gongs and the traffic gates lowered.
Barrier gates are lowered.
Span locks are withdrawn and movable span leafs open.
Navigation lights turned on to allow vessel passage.
Steps reversed to close the bridge after vessel passage.
Figures Illustrating Various Movable Bridges and Components:
(schematics from Movable Bridges by Michael Abrahams PBQ&D, Inc.)