## Prelim Deck
| Revision Date: | 2011-03-03 | Author: | Raymond Fontana | Phone No.: | (203) 389-3123
Prepared by:
Comments
Assumptions: Deck forming plan has been approved, beams have been profiled and the correct blocking points transferred to the top of beams. Checklist does not include specific requirements for hot weather and cold weather conditions and procedures. Following list in no particular order.
Spacing of bunks and deck support members
Rebar installation; size, spacing, splice lengths
Shear studs already installed and minimum field testing completed
Rebar clearances (1”-2”) minimum for bottom mat of rebar per plans
Expansion dam/joint; bonded out or included in placement, secured, cleaned, bonding agent if required
Rebar, expansion joints & tie-downs for parapet
Patch (tin) any over-sized opening in the deck caused by forming hardware or other gaps
Weep holes; secured, size, location, spacing, mesh or fabric over opening
Chamfered haunches if required and width of haunch checked
Deck should be blown-off, free of any debris, cigarette butts, tie wire, tools, etc.
Final check all blocking points 24 hours before scheduled placement – adjust as needed – not easily adjusted after majority of deck is secured
Stability of the screed rail and straightness of rails checked
Mechanical screed checked for deck thickness and cross-slope – dry run required, back-up motor recommended
Cross slope can be a straight grade or multiple breaks
Termination points (locations on span or spans with minimum bending moment if placement is terminated)
Keyway (male or female) and waterstop if required on deck overhang checked for alignment, dowels, etc.
Drip-notch on underside of deck if required
Overhang blocking points (sloped or horizontal)
Check for all embedments; conduits, scuppers, mechanical splices for location, line, grade, etc.
Location of pump truck(s), is assistance (troopers) needed to move pump truck if required
Back up pump truck or method of placement if pump truck fails
Generator and backup generator for lights and vibrators
Shielding and poly in place over live traffic are troopers’ needs for traffic control or equipment moves
Time of placement and weather conditions taken into account, cancellation procedure in place
Production rate anticipated (30-40 CY/HR); number of trucks, testing area, wash out area, turn around area, etc.
Admixtures in plant and in the field; determine all options and approval from lab
Working bridge on site, how many, finishing crew & tools
Wet cure procedure determined, burlap, poly, insulation blankets used as required and needed, enough on site
Proper securing of covered/insulated deck surface – material used (planks, rebar, etc,) to keep blankets in place can damage deck surface
Max/min thermometer required and placed
Any false-work embedment’s that will be removed should be greased
Removal of screed rail, vertical supports and patching of holes
Curing compounds or retarders allowed, if & when?
Water source approved for wet cure and control of runoff
Monitoring of ambient and deck temperatures over nights and weekend