## Steel Erection
| Revision Date: | 2011-03-03 | Author: | Mary Baier | Phone No.: | (860) 594-3256
Prepared by:
Comments
Drawings
Are the drawings stamped by a Professional Engineer Licensed in the State of CT?
Does the plan show all permanent and temporary structures?(i.e. railroad tracks, road, navigable waterway, etc.)
Can the erection sequence take place with in a reasonable time frame, in accordance with any limits of operations set forth in the contract? If not, are temporary supports adequate?
Are the crane locations depicted?
Delivery locations of members noted.
Member marks should be the same as shop drawings, if not, is a key provided?
Is there an erection sequence?
Are temporary support conditions clear, such as holding crane locations, strongbacks, including bolted and welded connections, etc?
Are rigging requirements suggested, does it show the Center of gravity for the members?
Capacity charts for cranes, including maximum radii allowed, and boom length are vital.
Handling procedure for any member that has a lifted length divided by width (L/b) greater than 85.
Any blocking requirement for bridge bearings?
Splicing requirements, are they realistic?
Steel Erection over Railroad
Railroad has reviewed and approved Contractor-shop drawings and erection plans?
Latest crane inspection included?
Are the applicable safety factors included?
Can the installation anticipated take place within the appropriate time frame for track and/or electrical outages? If not, temporary bracing adequate?
Steel Erection on Navigatable Waterways
Configuration of the barges included, loading sequence, stability provisions?
Anticipated locating of barge during erection sequence included?
Calculations
Design calculation should indicate load capacity and verify stability of members, temporary supports, and cranes for each pick(Hybrid members, tall webs-thin flanges are problematic).
Calculations should include structural adequacy and stability for each step of bridge assembly.
If contractor fabricated erection rigging is used, such as lift beams, spreader beams, clamps, calculations should be included for each element anticipated.
Pre-engineered devices such as clams, manufacturers certification or catalog cuts are adequate.
Coordination
Has a meeting taken place with all stakeholders?
Do other agencies have to review and comment on the plan (Railroad, USCG, harbor master, local traffic engineer, Designer,etc.)
Do any other activities have to be coordinated with the steel erection? Setting forms, bearings installation?
Review bearing installation temperature restrictions, is there a corrective procedure, if the steel erection takes place outside of these contract requirement?
Coordination with the Rocky Hill lab on steel member testing or welding card inspection/testing.
Pre-engineered devices such as clams, manufacturers certification or catalog cuts are adequate.
Field Inspection
Check all personnel certifications - crane operator, welders, etc.
Check all equipment certifications - cranes
Check fall protection requirements and installation
Check crane position, should be painted right on road or mats.
Check crane radii
Check temporary supports against installation procedure
Check bolts and pins, is the minimum installed?
Monitor bolt installation procedure
Check field weld size, geometry, etc.
Check bearing alignment/adjustment
Field reeming of bolt holes are not allowed unless approved by the Engineer. (Anything greater then 10% of the connection should be addressed by the Engineer of record)