## Structural Concrete
| Revision Date: |  |  | 2014-11-28 | Author: | Anthony Kwentoh | Phone No.: | (860) 594-2673
Prepared by:
Comments
Transportation and Delivery of Concrete
The producer is to have enough plant capacity and trucks to ensure delivery at the rate required to prevent cold joints from forming. A preplacement meeting may be required.
If there is a malfunction, manually written tickets with all required information are allowed for up to 1 hour.
If the concrete mix arrives with a slump lower than allowed, water may be used to temper mix.
The concrete must be completely discharged into the forms within 1 and 1-1/2 hours from the batch time stamped.
The temperature of concrete mixture during placement is to be between 60°F and 90°F.
Acceptance Testing and Test Specimens
Samples of concrete are to be taken at the discharge end of the concrete pump at the point of placement.
Refer to Specification Section 6.01.03-4(a) for testing limits for the different concrete mixes.
The distance from concrete placement and concrete testing and initial curing should be 100 feet or less.
After initial curing, the test specimens are to be stored in a cylinder curing box and specimens are to be transported to the Divisions of Material Testing.
Additional specimens may be cured with the structured in the field.
Compressive Strength Specimens
The sample is to be taken at point of placement into forms from one or more of the same truck loads.
A minimum of 2 cylinder results will determine in-place strength. Additional cylinders are to be taken for construction sequence.
Protection From Environmental Conditions
Placement of concrete cannot start or continue until there is adequate protection from the rain.
When the air temperature is above 90°F, forms coming in contact with concrete being placed have to be cooled below 90°F for a minimum of an hour before and after concrete is placed.
When the air temperature is below 40°F, a Cold-Weather Concrete Plan needs to be submitted.
Placement: Forms coming in contact with the concrete being placed have to be heated to a minimum of 40°F for a minimum of one hour prior to and maintained throughout concrete placement.
Curing: For the first 6 days, the concrete internal temperature has to be maintained to be no less than 45°F and the air temperature surrounding has to be maintained to be no less than 60°F.
Curing: For the next additional 8 days, the structure temperature has to be maintained above 40°F but no more than 90°F.
All concrete placed on bridge decks are to be protected from damage due to rapid evaporation.
No construction joints are to be formed between the levels of extreme low water and extreme high water or the upper limit of wave action.
Handling and Placing Concrete
A pour sequence should be defined on the plans for bridge decks. If not, an Engineering Clarification Memo (ECM) should be sent to the Lead Engineer.
Placement of concrete is to be done continuously between construction joints.
The delivery rate should be that fresh concrete is always placed before initial set occurs.
Platforms for workers and equipment are not to be supported directly on reinforcing steel.
Do not pour concrete for superstructure until substructure has achieved sufficient strength.
Concrete in arches are to be placed uniformly and symmetrically.
Aluminum is not to be permanently incorporated into the concrete.
Concrete is not to be dropped more than 3 feet above the forms to avoid segregation.
Concrete is to be discharged directly over beams or girders.
All concrete is to be sufficiently consolidated by vibration immediately after placement.
Vibrators are not e used to shift fresh concrete horizontally.
Vibration is not be applied directly to reinforcement, hardened concrete, ornamental molds, form liners, or embedded items.
CAUTION: Do not allow overvibration of concrete resulting in visibly excessive air bubbles and/or laitance in concrete indicating segregation of materials.
Screed and runway supports are not to be located on any stay-in-place metal form sheets, form supports, and reinforcing steel.
Only 2 passes of the transverse screed are permitted.
The placement sequence is to proceed so that the total deflection will occur before initial set.
Concrete is not to be placed against the previously placed concrete for at least 12 hours without the Engineer's approval.
Concrete may only be under water within a cofferdam using a mix designed for this application.
For underwater concrete mixes, a minimum of 10% additional cement will be required.
Underwater concrete is to be placed continuously and as horizontal as practical.
Placement can begin following inspection and acceptance of the depth and character of the foundation material.
Each succeeding layer is to be placed before the preceding layer has taken initial set.
For large concrete placements, more than one pump may be used.
To prevent segregation, underwater concrete is to be placed in compact mass, in its final position, using a pump, and is not to be disturbed.
Cofferdams are to be vented during the placement and curing.
If a tremie is used, it is to have watertight couplings.
For mass concrete placements, the mix temperature is not to exceed 85°F at point of discharge.
Finishing Plastic Concrete
All concrete surfaces not against forms are to be struck-off to the planned elevation or slope.
The surface is to be finished by floating with an acceptable tool.
All construction and expansion joints are to be tooled with an edger.
Joint filler is to be left exposed.
For at least 12 hours after the concrete has set, no equipment is to be operated in the immediate vicinity of the freshly placed concrete.
Water is not to be added to assist with finishing concrete.
All finishing work is to be performed from work bridges supported above the deck surface.
Surfaces covered with waterproofing membrane are to be finished with a smooth surface, free of mortar ridges and other projections.
Concrete wearing surfaces need a skid-resistant texture by dragging, brooming, tining, or a combination.
The entire surface is recommended to be checked with an acceptable 10-foot straightedge.
The surface is not to vary 1/8 inch in 10 feet for decks not to be covered with an overlay.
The surface is not to vary 1/4 inch in 10 feet for decks to be covered with an overlay.
Bearing Surfaces
Concrete surfaces under metallic masonry plates and elastomeric bearings are to have a float finish.
After concrete has set, the area which will be in contact with the masonry plate is to be ground.
The finished surface is not vary more than 0.0625 inches in 10 feet.
Curing Concrete
The duration of the initial and final curing period is an uninterrupted 7 days at minimum.
Concrete may be cured in forms by keeping the forms in place without loosening.
Concrete may be kept continuously wet by ponding, spraying, or covering with thoroughly wet material.
Concrete may be covered with a waterproof sheet material to prevent moisture loss.
Additional Requirements for Curing Concrete for Bridge Decks
The Contractor has to submit a curing plan 14 days prior to placement.
A water fog spray is to be used from initial placement until the final curing period begins.
The entire concrete surface is to be covered with a water-retaining material that shall be kept saturated.
The internal temperature of the concrete is to be monitored with a calibrated continuous recording thermometer for a minimum of 7 days.
The air temperature between the concrete surface and its protective covering is to be monitored with one recording thermometer.
Finishing Concrete Structures
All cavities is to be filled with cement mortar of the same proportions used in the body of work. If exposed, cement mortar needs to be of uniform color.
Any minor repairs due to irregular projections are to be done immediately following the removal of forms.
Construction and expansion joints are to left carefully tooled and free of mortar or concrete.
The cavities produced by form ties are to be cleaned, saturated with water, and pointed and trued.
Mortar used in pointing is to be used within one hour of mixing.
Finishing work is not to interrupt the curing period.
Concave surfaces where water will be retained is not allowed.
The mortar or grout is to completely fill and to be tightly packed into recesses and holes.
All surfaces of mortar or grout is to be cured no less than 3 days.
Joints are to be cleaned and dried before sealing is applied.
The sealing is to be flush with or no more than 1/8 inch above the adjacent surface of concrete.
Application of Loads
Loads are not to be applied to concrete structures until the concrete has attained sufficient strength in accordance with the specification.
Backfilling cannot begin until concrete has reached 80% of its specified strength.
No live or dead loads are allowed on concrete structures that exceed the reduced load carrying capacity.
For post-tensioned structures, no live or dead loads are allowed on any span until the steel has been tensioned.
Precast concrete or steel girders are not to be placed until concrete has attained 85% of its specified strength.
No load is allowed on mortar or grout that has been in place less than 72 hours.
The concrete deck will not be opened to traffic until its attained its full strength.
Pay Factors (Confirm with your Contract Specification first.)
Air Pay Factors
Strength Pay Factors
Total Adjustment