## Traffic Signals
|  | Revision Date: |  | 2013-05-03 | Authors: | Wail Allababidi | Phone Nos.: | (860) 258-4619
[6 empty] | Jacek Brodowicz |  | (860) 633-2331
[6 empty] | Jeffery Knapp |  | (203) 785-8082 ext. 113
Prepared by:
|  |  | Project No.: |  |  | Date: | Location:
Comments
PHASE ONE: ORGANIZATIONAL PHASE (Administrative/Engineering/Procurement)
Request mark-out of state right of way performed by state surveys if needed.
The contractor will call "Call Before You Dig" (1-800-922-4455) to mark underground utilities at each intersection. (Test pits if needed.)
The contractor will submit catalog cuts, working drawings, and shop drawings as specified in Section 1.06 of the contract specs.
The contractor shall mark-out the proposed locations for all of foundations and traffic control devices as depicted on the plans, prior to the Walk-Thru Meeting(s).
The inspector will initiate a walk thru inspection inviting the designer (or consultant) from the electrical section, the designer (or consultant) from traffic, Newington Traffic, cooresponding utilitiy companies, Town/City Engineer(if applicable), and Contractor. The contractor will forward invintation to their representatives (ie. camera manufacturers rep, controller manufacturer, etc.).
Traffic Signal Walk-Thru
Span Poles / Mast Arms: Determination of Foundation Locations…
Does Shaft have overhead obstructions (trees, wires, signs, etc.)?
At the proposed location does the Shaft Arm have PURA clearance distances between overhead wires?
Is the proposed arm length the correct length for the location?
Are the proposed signal head locations correct?
Camera Placement: Does the arm length for the camera need to be changed and/or moved? (The camera manufacturer's representative needs to be present at walk-thru since the specification reads that the final placement and alignment are to be at the determination of the manufacturer.)
Is the orientation of the bolt circle correct?
Where is the electrical service being fed from? (Manhole or pole; some poles are considered junction poles and service cannot come from junction poles.)
Place of foundation - Any ADA / PROWAG issues?
Pedestrian Push Buttons
Locations of the pedestrian buttons are to be within 10 feet of the handicap ramp in the direction of the line of walk.
ADA / PROWAG compliance?
Signal button (peds cross w/ green) or dual button (exclusive ped phase)?
Alignment of the Pedestrian Signal Head should be considered in determining the location.
Controller
Location of the controller - Does it have adequate protection?
ADA / PROWAG clearances of sidewalks?
Location of the meter socket: street side or field side?
Meter socket needs to be a minimum of 3 feet from curb to face of meter (Prior approval needed for 18 inch clearance.)
Number of conduit sweeps from where service is taken from to where the meter socket is (Electric code is a maximum of 4).
Orientation of the cabinet - The cabinet shall be built in a fashion that when the operator needs to service an intersection, they can stand within the doorway of the cabinet, in front of the main controller board, look up to see the signals, and not have to turn around to see them. Within some towns/cities there are double-door controller boxes so the orientation of the internal configuration becomes more critical.
Handicap Ramps
Are new ADA / PROWAG plan sheets incorporated into Project?
Location of handicap ramps in relation to existing catch basins, manholes, etc.
Can the handicap ramp be installed to ADA / PROWAG requirements (curb elevations, side clearance for wings, room for elevation changes, adjacent retaining walls or steps, fences, etc. near)? If there are any conflicts, seek direction from the Designer and insist on installing per ADA / PROWAG since federal money is involved.
Interconnect
Are there existing splice boots where called for?
Is there enough slack in the existing line to perform the splicing? (Splicing is done on ground, in a van.)
Does the existing overhead utilities comply with PURA guidelines? Adjustments are required to be done prior to attaching the new interconnect.
If exisiting underground conduit is to be used, is it there? Is it adequate size? (Wires are only allowed to occupy 40% of its opening, as per electrical code.) Is there an item to clean the conduit?
New Underground Conduit: What are the underground obstructions? Is there flowable fill as backfilling for other utilities nearby?
Has the designer provided revised plan sheets based on the findings from the Walk-Thru Meetings; significant changes do qualify for revised drawings to be provided.
The contractor will order materials when the catalog cuts, working drawings and shop drawings have been approved and/or reviewed.
The contractor will furnish all material certifications and samples needed for testing in order to have everything on the project ready prior to start of phase two.
The contractor is responsible for scheduling all work with utility companies (816, 10.00.12).
PHASE TWO: CONSTRUCTION INSTALLATION
The contractor and subcontractors are ready to start ground work. Trenching and backfilling, installation of rigid metal conduit (RMC), handholes, precast foundations and poured in place concrete foundations etc.
Should any sub-surface conditions occur during the installation of Mast-Arm and/or Span Pole Foundations; consult both Bridge Design And Soils for guidance.
Pull electrical conductor wires through RMC.
Install new steel span poles / mast arms.
Check dates on LED lamps for traffic and pedestrian signals to ensure they are installed no later than 12 months after fabrication date.
Handholes are installed on a 12" minimum gravel bed.
Loop sawcuts - cheseled corners, installed in good pavement, tubing or foam backer rods wedged in sawcut so cable does not float to top when sealant is applied.
All signing and pavement markings have been installed according to plan.
The contractor will request electric service from the power company (e.g. CL&P).
Install overhead traffic signals on span wire or mast arm then cover them with plastic bags.
Contractor performs Preliminary Functional Test (816, 10.00.10(2)b.2). At existing traffic signal locations, if test is successful, then contractor may turn on new signals and take down old signals. At new signal installations, signal may be put on flashing operation but may not flash longer than 7 days.
Inspector performs Visual Final Inspection (816, 10.00.10(2)b.1). Results are noted on the Preliminary Inspection Checklist, available from the Traffic Electrical Unit.
Request for 30 days test on new signals inviting traffic and electrical design section to perform the Functional Inspection (816, 100.00.10(2)b.3) and start the 30 day test for each intersection inspected. If no problems are encountered during this period then responsibility for the operation of the signals will pass to the state. If there are problems with the signals during this period then the contractor will make repairs and a new 30 day test period will start from the day repairs are made.
State traffic and electrical design as well as electrical maintenance will generate a punch list for corrective work then they will forward their comments to the inspector. The inspector will notify the contractor who will then perform the corrective work.
Upon completion of the punch list items, a semifinal inspection will be performed by the project engineer and supervising engineer.
Final inspection by the project engineer and supervising engineer.