## Utility
| Revision Date: |  |  | 2011-03-03 | Author: | Vicent D'Aleo | Phone No.: | (860) 585-2741
Prepared by:
Comments
Design Phase
Are existing utilities as shown on plans?
Are utilities to be maintained during construction? If so, are provisions in place?
Are utility agreements required? If so, are they in place?
Must utilities be moved? If so, is relocation shown?
If temporary supports indicated, is project constructible?
If no relocations are shown, is project constructible?
Are there any underground utilities shown/not shown? Will they affect construction? If so, have they been addressed?
Are there any substations or utility appurtenances within construction area required to be accessed during construction? If so, have provisions been included in specifications.
Are relocations extensive enough to request an early order to start for utilities?
Will overhead utilities be in conflict with proposed permanent construction and/or the use of construction equipment such as cranes or pile drivers? If so, they should be relocated.
If over railroad, is casing required? Is utility to be bonded and grounded?
Are pole relocations in conflict with proposed sidewalks?
Preconstruction Phase
Go to “Utility” website to obtain the Utility Project Engineer and Supervising Engineer assigned to the project. Contact them for any questions regarding utility agreements and notify them of the preconstruction meeting. You can also obtain utility addresses and manager contacts for each utility.
Review contract plans and specifications to review utility plans and obtain name, title and telephone number of the utility representatives.
Obtain Utility Agreements. Confirm that all agreements are in place for each utility company that is required to perform work on the project.
Review utility agreements and compare to the contract plans to make sure there are no discrepancies.
Send letter to utility representatives to notify them of the preconstruction meeting.
Preconstruction Meeting: The assigned District personnel shall review and discuss the following utility issues:
Brief review of agreement - including the amount, the percentage of reimbursement to the utility, and a summary of the work to be performed.
Survey requirements to be completed prior to start of utility work.
Schedules, start dates, and time needed to complete work.
Maintenance and Protection of Traffic requirements.
Administrative requirements - review who will be submitting the Con-40’s and who will be responsible for review and signature. How will the Con-40’s be sent to the field and then returned to the utility companies.
Schedule a field utility meeting to layout poles. Determine the day and time for a bi-weekly or monthly utility meetings to be a part of the progress meetings.
Permit and Start Relocation Letter
Once a start date is determined for the utility companies a Permit will be prepared and processed. The permit will be signed by the manager of the Districts Permit Section.
A Start Relocation letter notifying the utility companies they are approved to start and that funding is available will be prepared and processed. This letter is signed by the District Engineer. The permit will be attached to this letter and sent to the utility companies. The utility is required to sign the permit and send copies back to the district for their files.
Construction Phase
Utility Meetings The assigned district personnel shall review and discuss the following topics for each utility: (These items and discussions will be included in the minutes of the progress meeting, utility portion)
Current status of the utility work
Each utility companies estimate of percent complete
Problems or delays in accomplishing the work
Current budget status as reported by the utility.
Anticipated completion date.
Anticipated changes to the utility plans.
Anticipated change in scopes and reasoning.
Anticipated cost overruns as reported by each utility.
Status of submission of Con-40’s.
Con-40 and Con -41 Inspection and Review A Con-40 shall be used for labor, equipment and materials permanently installed on the project. A Con-41 shall be used to report all temporary material installed and temporary and existing material removed from the project.
NOTE: An ISP form is used in connection with the Metro-North Railroad invoices.
The Chief Inspector should require that each utility check in at the start of each workday. Providing the work force, major equipment location, and nature of work.
The inspector should note on the inspector’s daily report or DWR in Sitemanager the name of the utility company (or subcontractor), labor, equipment, major materials (poles, manholes, conduit), location, number of hours, and nature of work.
The Utility Company must prepare and provide a Con-40 for their crews as well as a separate Con-40 for their subcontractor’s to include labor, equipment and materials.
Each Con-40 and Con-41 must include:
Utility name
Utility subcontractor (if applicable)
Date(s) of the work
Project number
Labor: classification of employee(s), number of employees, and total hours of work (All OT must be clearly shown)
Equipment: type, manufacturer, model, equipment # (if available), size, and total number of units
All major and minor materials installed
The Inspector should verify that the work included on the Con-40 was actually performed by comparing it to the inspector’s daily report or the DWR in Sitemanager. The inspector should only sign in the DOT signature box if they agree that the information in the Con-40 and Con-41 appear reasonable and appropriate. The chief inspector should attempt to resolve the discrepancies with the utility representatives. If the discrepancies cannot be resolved, the chief inspector should include an explanation within the body of the Con-40 or Con-41 as to why they do not approve of the work and sign under the explanation (if inspector’s do not approve of the work on the Con-40 or Con-41 do not sign in the DOT signature box). Copies of the Con-40’s shall be provided to the following:
One Copy to the Utility Company Representative
One Copy to the District Utility Coordinator
One Copy to the Project records
Original sent to the Financial Services Unit.
Changes to Utility Agreements
Cost Overruns – include any increases to the original estimate for labor, equipment or material costs or quantities. These are for costs that were underestimated or inadvertently overlooked by the utility company and not due to any changes in the State’s plans or design.
Cost Underrun – include any decreases to the original estimate for labor, equipment or material costs or quantities. These are for costs that were overestimated by the utility company.
Change-In-Scope - include any increases to the original estimate for labor, equipment or material costs or quantities incurred by the utility company, due to changes to the plans or design initiated by the State.
Overtime Request – A request for overtime must be submitted by the utility company to the District Engineer for approval.
All Cost Overruns, cost underruns, change-in-scopes and overtime requests must be submitted by the utility company to the District Engineer. These requests must include a detailed explanation and estimate of cost.
The District utility coordinator is responsible to prepare and process these letters. The Project Engineer, chief inspector, and/or the utility engineer will provide assistance to determine the validity of the request.
If the district determines that the request is to be authorized, the district must review funding needs with financial services for approval. If additional utility funds are needed then a project mod. must be completed. A reconciliation sheet to request additional utility money must be completed by the Project Engineer and sent to the fiscal representative for a project mod. to be completed.
The Project Engineer/Utility coordinator will process the authorization of Change-in-scope/Cost Overrun/Cost underrun letters for signature by the District Engineer.
The Utility section and financial services must be copied on each letter.