## WSA
| Revision Date: | 2011-03-03 | Author: | Richard Unkel | Phone No.: | (203) 752-0113
Prepared by:
Comments
How to Properly Store Waste Materials
Review the Notice to Contractor – Environmental Investigations
Note the Areas of Environmental Concern
Note the CTDEP groundwater classification beneath the site
Note presence of specific compounds
Note Low-Level Areas of Environmental Concern
Obtain Task 210 Report from Environmental Compliance
Review approved Health & Safety Plan and Environmental Health and Safety specification
Review specification Securing, Construction and Dismantling of a Waste Stockpile Area
Review environmental plan sheets noting locations of proposed Waste Stockpile Area
Review plan sheet details
Note Areas of Environmental Concern and Low-Level Areas of Environmental Concern locations on plans
Construction blocks must be solid precast rectangular blocks measuring 6 feet in length, 3 feet high and 2 feet deep.
Poly plastic sheeting for underlayment shall be 30 mils thick and a minimum of 10 feet wide. The sheeting covering the piles of excavated material must be 10 mils thick and minimum 10 feet wide.
Sand bags must be a minimum of 30 pounds in weight to secure the poly sheeting to cover the soil piles.
Bedding sand conforms with 816 standard Section 6.51.02.
Processed aggregate conforms with appropriate 816 standard Section 3.04.
Hay bales conform with 816 Section 2.18.
Bituminous concrete complies with 816 Section 4.06.
Roll off storage containers shall be watertight, steel body construction and of adequate size to handle storage and subsequent transportation of material to the proper disposal facility.
Build WSA at location shown on plans.
WSA must be built prior to start of any excavation activity within the AOEC.
Proposed location of WSA must be cleared of any debris and vegetation and any objectionable materials removed that may injure the polyethylene underlayment must be removed prior to placement of Controlled Materials.
Compliance with CTDEP “General Permit for Contaminated Soil/Sediment Management (Staging or Transfer) including general operating conditions. Refer to the Special Provision.
How to Properly Handle Waste Materials
All loads must be accompanied by a manifest for each individual hauling vehicle.
Each individual manifest must by signed by the consultant assigned to the Project by the Office of Environmental Compliance.
The disposal facility to receive the Controlled Materials must be on the CTDEP approved list. Check with the Office of Environmental Compliance or the CTDEP website.
Any stockpiled Controlled Materials slated for re-use onsite in a structural area must be tested (gradation and proctor) from an Office of Environmental Compliance consultant laboratory.
Material generated must be from the AOEC’s noted in the Contract documents.
Review the Contract Special Provisions for Controlled Materials Handling. This specification will supplement the excavation items listed in the 816 and the Contract Special Provisions whenever contaminated materials are encountered.
Review the Notice to Contractor – Environmental Investigations.
All required materials are detailed on the Project plans and shall conform to the requirements of the Contract.
Polyethylene plastic sheeting must be minimum 30 mils thick and sheeting covering the excavated material shall be a thickness of 10 mils. All sheeting must be 10 feet wide.
All containers shall be watertight, steel body construction with the ability to handle the storage and subsequent transportation to the disposal facility.
Covers for the containers must be of polyethylene sheeting or similar watertight material and sufficient in size to completely cover the top opening and securely fastened to the container.
Sand bags to secure the covers must weigh 30 pounds.
Sorbent booms shall be 8 inches in diameter and 10 feet long and possess petrophilic and hydrophobic properties. These booms must have device for connections of additional length of booms.
Employ methods in the Health and Safety Plan when encountering Controlled Materials.
All Controlled Materials when excavated must be transported to the waste Stockpile Area unless noted otherwise in the Contract documents.
WSA must be operating and constructed in accordance with the Contract prior to receiving loads of Controlled Materials.
Excavated materials must be staged in accordance with the Contract documents.
All stockpiles must be secured at the end of the work day and inspected daily by the Contractor and inspection staff.
Inventory all materials stockpiled at the WSA on a daily basis.
Employ the proper dust control procedures, dewatering and decontamination procedures as outlined in the Contract documents.
Refer to the Contract documents for adherence to the CTDEP General Permit for Contaminated Soil/Sediment Management (Staging and Transfer) in the Contract documents.
Ensure that no additional material is tracked by hauling vehicles or equipment beyond the WSA.