## CONSTRUCTION
ACTIVITY | INTRANET LINK | DATE REQUESTED/ | DATE COMPLETED/
|  | FORWARDED | RECEIVED/APPROVED
General Information | CADD File Release Form.doc
Electronic File Disclaimer.pdf
Develop Pre-Construction Meeting | SAMPLE:
Talking Points Document | PreConstruction Meeting Topics.doc
Develop Contractor Submittal Log | Submittal Log.xls
Develop Contractor Submittal Letter | Submittal Transmittal Memo.doc
Review Contractor Submittals
High Performance Building | http://www.ct.gov/dcs/cwp/view.asp?a=4224&q=491240&dcsNav=¦
"Construction Substitution Reports"
Prepare
Submit to DCS and OPM
RFI's/RFC's | RFI-RFC Log.xls
FDC's (Principal Engineer's Signature)
Engineering Bulletins (same as FDC) | ENGINEEERING BULLETIN blank.doc
Change Order Preparation | Intranet: Digital Project Development Manual
Designer Inspections
Above Ceiling | SAMPLE: Above Ceiling Checklist - sample.xls
Semi-Final | SAMPLE: Above Ceiling Checklist - sample.xls
High Performance Building | http://www.ct.gov/dcs/cwp/view.asp?a=4224&q=491240&dcsNav=¦
"Pre-Occupancy Commissioning
(Cx) Report"
Prepare
Submit to DCS and OPM
Receive Certificate of Code Compliance
Form from Department's AHJ (on
Non-Threshold Projects)
Designer needs to sign 2 original copies | Consultant Design and Construction Sign-off
Contractor needs to sign 2 original copies | Consultant Design and Construction Sign-off
Transmit back to Department's AHJ
Review Closeout Documents
Checklist | Complete Projects Checklist.xls
High Performance Building | http://www.ct.gov/dcs/cwp/view.asp?a=4224&q=491240&dcsNav=¦
"Post-Occupancy Commissioning
(Cx) Report"
Prepare
Submit to DCS and OPM
Complete Energy Efficiency Design
Rebate Process
Store Project Files at Pascone Place
(6 Months after the end of Construction
or after Outstanding Claims Resolved)
RSL Guidance | RSL Guidance - full.pdf
Prepare Record Storage List (RSL) | RSL50-108 (Blank.xls)
Transmit RSL | Store Files at Pascone Memo.doc
Prepare PRO-54 when RSL Returned | PRO-54