## Sheet1
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (pag 1 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
19100 |  | General Commisioning Requirements
| 1.7A |  | x | x | x | x
25613 |  | Vapor Barrier
| 3.4A | Non Destructive Seam Testing | x |  |  | x
33000 |  | CIP Concrete
| 3.8A | Rebar/ Forms/ Inbeds |  |  | x
| 3.16 | Steel Rienforcement |  |  | x
|  | Bolts/ Studs |  |  | x
|  | Concrete Placement |  |  | x
|  | Curing |  |  | x
|  | Air/ Slump |  |  | x
|  | Cylinders |  |  | x | x
48100 |  | Unit Masonry Assemblies
| 3.12A | DOT Test A-I
|  | Lauyout and Rienforcement |  |  | x
| 3.12D/G | Grout Cubes (1 set per 5ksf) |  |  | x
| 3.12E | CMU Physical sample |  |  | x | x
| 3.12F | Mortar ASTM C780 |  |  | x
| 3.12H | Masonry Prism Test |  |  | x | x
| 3.12I | Wall penetration Test ASTM C1601
51200 |  | Structural Steel Framing
| 1.2E | Surveyor base Plate/ Bolt verification | x |  |  | x
| 1.3H | Testing |  |  | x | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 2 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
51200 |  | Structural Steel Framing (continued)
| 2.8A | Shop Reports |  |  | x | x
| 3.2A | Field Inspection |  |  | x
52100 |  | Steel Joist Framing
| 3.3A | Field Inspection |  |  | x | x
53100 |  | Steel Decking
| 3.5A | Field Inspection |  |  | x
54000 |  | Cold Formed Metal Framing
| 3.6A | Field Inspection |  | x |  | x
55000 |  | Metal Fabrications
| form 816 | shop inspection and field welding inspection |  |  | x | x
55200 |  | Portable Railing System
| form 816 | shop inspection and field welding inspection |  |  | x | x
70800 |  | Commisioning of Thermal & Moisture
| 2.1A | Functional Performance Testing | x |  |  | x
| 3.1A1 | Fluid Applied Water Proofing | x |  |  | x
| 3.1A2 | Fabricated Wall Panel System | x |  |  | x
71900 |  | Water Repelants
| 3.1B | PH Levels of Concrete prior to water repelant | x
72100 |  | Thermal Insulation
| 1.4D | Thermography Test |  | x
| 3.8 | Thermography Test |  | x |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 3 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
72700 |  | Air Barriers
| 3.5A(1-13) | visual various inspections |  |  | x
74100 |  | Metal Panels
| 3.6A | Water Spray Test |  | x |  | x
| 3.6B | Mfg Rep Report | X |  |  | x
75419 |  | PVC Roofing
| 3.8A | Electric Field Vector Mapping |  | x |  | x
| 3.8B/C | Mfg Rep Report |  | x |  | x
78413 |  | Penetration FireStopping
| 3.4A/B | Visual |  |  | x | x
78446 |  | Fire Resistive Joint Systems
| 1.3G | Field Quality Reports |  | x |  | x
| 3.4A/B | Visual Review |  | x |  | x
79200 |  | Joint Sealants
| 1.4C | Adhesion |  | x |  | x
80800 |  | Commisioning of Openings (functional Perf Test)
| 3.1A1 | Metal Doors | x |  |  | x
| 3.1A2 | Alum Framed Entrances | x |  |  | x
| 3.1A3 | Insulated Transluscent Sandwhich Skylight | x |  |  | x
83313 |  | Coiling Counter Fire Doors
| 3.3A1-3 | Factory Mfg Start Up | x
|  | Test in Conjunction with Fire Alarm System | x |  |  | NFPA72
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 4 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
83323 |  | Overhead Coiling Doors
| 3.3A | Mfg Start Up | x
83613 |  | Sectional Doors
| 3.3A | Mfg Start Up | x
84523 |  | Fiberglass Sandwich Panel Assemblies
| 3.3A | Water / Spray Pen |  | x |  | x
85113 |  | Aluminum Windows
| 3.3A | Water/ Air Infiltration |  | x |  | x
86200 |  | Unit Skylights
| 3.3B | Water Leak |  | x |  | x
86250 |  | Tubular Daylight Device
| 3.3B | Water Leak | x
89100 |  | Louvers
| 1.1B2 | Tie into FA system/ BAS System | x
92900 |  | Gypsum Board
| ? | inwall inspection |  |  | x
95123 |  | Acoustical Tile Ceiling
| ? | above ceiling |  |  | x
96519 |  | Resilient Tile Flooring
| 3.2B3 | Alkalinity and Adhesion | x |  |  | x
| 3.2B4 | Moisture | x |  |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 5 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
96723 |  | Resinous Flooring
| 3.1B3A | Substrate Chloride | x |  |  | x
| 3.1B3B | Substrate Plastic Sheet | x |  |  | x
| 3.1B3C | Substrate Rel Humidity | x |  |  | x
| 3.1B4 | Alkalinity and adhesion | x |  |  | x
| 3.3A | Material sample | x |  |  | x
| 3.3B | Core Sample | x |  |  | x
110000 |  | Gen Requirements for Relocated Equipment
| 3.5F | Test/ Recommision | x |  |  | x
111000 |  | Vehicle Service Equipment
| 3.5A | Hydro
|  | Lube Pump and Pipe | x
|  | Bulk Oil Storeage and Pipe | x
|  | Anti Freezeand Pipe (FD12) | x
| 3.5B | gen test prep
|  | Lube Pump and Pipe | x
|  | Bulk Oil Storeage and Pipe | x
|  | Anti Freezeand Pipe (FD12) | x
111300 |  | Appliances
| 3.3A | test | x
111400 |  | Vehicle Washing Equipment
| 3.2 | Mfg start up | x |  |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 6 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
132160 |  | Installation of New Fuel Facility
| 3.1D | Underground electrical inspection | x
| 3.7A1 | Tank Hydrostatic | x
| 3.7A2 | Tank Piping Hydrostatic | x
| ? | Fuel Master Statem (Mfg Start Up) | x |  |  | x
| OSFM/NFPA | Gas Station Start Up dispensing,emergency stops, shunt trip disconnect | x
Emergency phone, intercom, etc.
132180 |  | Tank Monitoring System (Gas Station, Gen Tank, O/W Sep)
| 3.3B1 | Start UP and acceptance | x |  |  | x
133419 |  | Metal Building (Cold Storage Building )
| 1.5E(9) | Field QC Report | x |  |  | x
| 1.5F | Final Survey | x |  |  | x
| 2.13A,B | Shop Inspection |  |  | x | x
| 3.1 | exam report (endorseed by erector) | x |  |  | x
| 3.1B | Land Survey prior to erection | x
| 3.9 | Field QC (Bolting, welding ) |  |  | x | x
139000 |  | Paint Spray Booth
| 3.3 | Mfg Start Up | x |  |  | x
144500 |  | Vehicle Lifts
| 3.3 | Load Test | x |  |  | x
146010 |  | Hoists and Cranes
| 3.3 | Load Test | x |  |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 7 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
210548 |  | Vib & Seizmic (Fire Suppression Pipe & Equip)
| 1.4A | Seiz |  | x |  | x
211100 |  | Facility Fire Suppression Water Service Piping
| 3.6B | 24 hour static test | x
| 3.6C | Hydrostatic test 2 hours | x
| 3.8A | Flush chlorinazation | x |  |  | x
| 3.8A3d | Water sample/ potability | x |  |  | x
211313 |  | Wet Pipe Sprinkler System
| 1.5G | FH Flow test | x |  |  | x
| 3.9B | Leak Test, Controls, valves and FA Cross Ref | x |  |  | x
| 3.B3 | Acceptance Testing/ Cross ref FA System | x |  |  | x
211316 |  | Dry Pipe Sprinkler System
| 1.5G | FH Flow | x |  |  | x
| 3.7B1 | Leak Test | x |  |  | x
| 3.7B2 | Controls, valves, safties | x |  |  | x
| 3.7B3 | Acceptance Testing/ Cross Ref FA System | x |  |  | x
213116 |  | Diesel Drive Centrifical Fire Pumps
| 3.6A | Test in Compl with 213900 | x |  |  | x
| 3.6B | Mfg start up | x |  |  | x
| 3.6D | Leak, Operational,Controls | x |  |  | x
213400 |  | Pressure Maintenance Pumps
| 3.2A | Mfg rep Start Up | x |  |  | x
| 3.2B | Operational, Pressure, Controls | x |  |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 8 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
213900 |  | Controllers for Fire Pump Drivers
| 3.6B | Mfg Start Up | x |  |  | x
| 3.6D | Test Prep | x
| 3.6E | Accept Test, after Hydro Test and Flush | x |  |  | x
220548 |  | Vib & Seizmic (Plumbing Pipe and Equipment)
| 1.4A | Per IBC | x |  |  | x
220719 |  | Plumbing Piping Insulation
| 3.9A/C | Visual |  | x |  | x
220800 |  | Plumbing System Commisioning (Dom Hot Water)
| 3.5A | Functional Testing | x |  |  | x
221100 |  | Plumbing System Pipe, Fittings, Valves
| 3.9A | Rough in | x
| 3.9B | Dom water pressure | x
| 3.9C | DWV rough and Head Test | x
| 3.9D | Comp Air | x
| 3.9E | Gas | x
| 3.11A | Clean Potable Dom Water Pipe | x
|  | Potability Test |  | x |  | x
| 3.11B | Clean Non Potable Water Pipe | x
221119 |  | Domestic Water Piping Specialties
| 3.3A | BFP | x |  |  | x
221123 |  | Domestic Water Pumps
| 3.5A | mfg start up | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 9 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
221319 |  | Sanitary Waste Piping Specialties
| 3.5A | Leak test | x
221325 |  | Oil Water Separator
| 3.6A | Hydro | x |  |  | x
| 3.6B | Pipe test | x |  |  | x
221519 |  | Gen Service Pack Air Compressor and Receivers
| 3.4A | Mfg Start Up | x |  |  | x
223300 |  | Electric Domestic Water Heaters
| 3.4A1 | Leak | x |  |  | x
| 3.4A2 | Operational | x |  |  | x
| 3.4A3 | Controls | x |  |  | x
223400 |  | Fuel Fired Domestic Water Heaters
| 3.4A2 | Leak | x |  |  | x
| 3.4A3 | Operational | x |  |  | x
| 3.4A4 | Controls | x |  |  | x
224200 |  | Commercial Plumbing Fixtures
| 3.12A1 | Emergency ey test mechanical | x |  |  | x
| 3.12A2 | Leak, Operational, Controls, | x |  |  | x
| 3.12D | Water tempering | x |  |  | x
| 3.12B | Water cooler test | x |  |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 10 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
230548 |  | Vib & Seizmic (HVAC)
| 1.5A | IBC | x |  |  | x
230593 |  | Test, Adjust, Balancing
| 3.3 | Air, Hydronic, Sound |  | x |  | x
| 3.19A | Construction Phase |  | x |  | x
| 3.19B | Status Report |  | x |  | x
| 3.2 | Final Test |  | x |  | x
| 3.22A | 90 Day TAB Revisit |  | x |  | x
| 3.22B | Seasonal Added |  | x |  | x
230800 |  | HVAC Systems Commisioning
| 3.7 | Functional perf test | x |  |  | x
230900 |  | Inst and Controls for HVAC
| 3.6A | Mfg start up | x |  |  | x
230923 |  | Control Valves
| 3.9A-D | Functional | x
230925 |  | Control Dampers
| 3.7/8 | Chechout | x
232113 |  | Hydronic Piping
| 3.7B | Pressure | x |  |  | x
232123 |  | Hydronic Pumps
| 3.5A | Mfg start up | x
232300 |  | Refridgerant Piping
| 3.7A,B | ASME B31.5 Chapter VI | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 11 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
232500 |  | Water Treatment
| 3.4A | Mfg start up | x
| 3.4B2-8 | Pressure, leak etc | x
| 3.4D | Sample Water | x |  |  | x
233113 |  | Metal Ductwork
| 3.7B | Leak test | x |  |  | x
| 3.7C | Clean test |  | x |  | x
233300 |  | Air Duct Accessories
| 3.2A1-5 | Functions | x
| 3.2A6 | FA Tie In | x |  |  | x
233423 |  | HVAC Power Ventilators
| 3.3A | Mfg start up | x |  |  | x
233600 |  | Air Terminal Units
| 3.6A1-4 | Mfg rep, leak, op, controls | x |  |  | x
233823 |  | Industrial Ventilating Equipment
| 3.3A | Mfg start up fume exhaust | x |  |  | x
| 3.3B | mfg start up mobile filtration | x |  |  | x
235216 |  | Condensing Boilers
| 2.5A-C | Burner, hydro (Source Test 14 day notice) | x |  |  | x
| 3.4A | ITA Oversee 3.4C2 | x |  |  | x
| 3.4C2 | Mfg start up Hydro, Controls, Operation | x |  |  | x
| 3.4G | Performance test | x |  |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 12 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
237313 |  | Energy Recovery 100% Outdoor Air Unit
| 3.1A | Copy shipped with unit (IOM) | x |  |  | x
| 3.6 | Mfg start up with BAS Contractor | x |  |  | x
237413 |  | Packaged Outdoor Central Station AHU
| 3.4A | Mfg start up | x |  |  | x
| 3.5 | Start up and controls | x |  |  | x
238126 |  | Split Systems A/C
| 3.3A | Mfg start up, leak, ops, controls | x |  |  | x
238236 |  | Fin Tube Radiation Heaters
| 3.4A | Leak test | x |  |  | x
238239 |  | Unit Heaters
| 3.4A | Operational test | x
238316 |  | Radiant Heating Hydronic Piping
| 3.3A,B | Mfg start up, leak, controls | x |  |  | x
260519 |  | LV Electric Power Conductors/ Cables
| 3.5B | Resistance |  | x |  | x
260526 |  | Grounding and Bonding for Electrical System
| 3.6B | Resistance |  | x |  | x
260543 |  | Underground Duct and Raceway for Electrical Systems
| 3.6A1-3 | Mandral | x
260548 |  | Vib & Seizmic (Electric)
| 3.5A-C | Load, deflection, isolation |  | x |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 13 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
260800 |  | Electrical Systems Commisioning
| 3.6A | Cross ref with CA lighting | x |  |  | x
260923 |  | Lighting Control Devices
| 3.5B | Cont /ops/label | x |  |  | x
260943 |  | Network Lighting Controls
| 3.6A/B | Dali loop resistance | x |  |  | x
| 3.7 | Commisioning | x |  |  | x
262200 |  | Low Voltage Transformers
| 3.4A | Mfg start up | x |  |  | x
| 3.4C | NETA / label |  | x |  | x
262413 |  | Switchboards
| 3.3A,B | Resistance/ continuity |  | x |  | x
262416 |  | PanelBoards
| 3.5B | Resistance/ continuity |  | x |  | x
262419 |  | Motor Control Centers
| 3.5A | Various electrical |  | ??? |  | x
262713 |  | Electricity Metering
| 3.3A | Mfg start up | x |  |  | x
| 3.3B | Load Test 8 hours | x |  |  | x
262726 |  | Wiring Devices
| 3.3A | Polarity and GFI | x
262816 |  | Enclosed Switches and Circuit Breakers
| 3.2B | CB injection |  | x |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 14 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
263213 |  | Engine Generators
| 3.4A | Factory Breakdown | x |  |  | x
| 3.4B | Load Bank Field 2 Hours | x |  |  | x
| 3.4B | Load Bank Field Full Load 2 Hours | x |  |  | x
263600 |  | Automatic Transfere Switch
| 3.3B | Mfg Start Up 1-6 | x |  |  | x
| 3.3B | Field Testing |  | x |  | x
| 3.3F | Infra Red 60 days after Occupancy |  | x |  | x
| 3.3F | Infra Red 11 months after Occupancy |  | x |  | x
264113 |  | Lightning Protection for Structures
| 3.3A/B | UL Inspection Report |  | x |  | x
264313 |  | Surge Protection for Low Voltage Power Circuits
| 3.3A | Mfg start up | x |  |  | x
| 3.3B | Startup Check/ Elect, Mech | x |  |  | x
265100 |  | Interior Lighting
|  | Nfpa e lights and exit signs | x
265600 |  | Exterior Lighting
|  | Nfpa e lights and exit signs | x
270000 |  | Premises Voice/ Data/ CATV Wiring
| 3.5AB | Wavetech |  | x |  | x
| 3.6(1-7) | UTP+ |  | x |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 15 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
275116 |  | Public Address and mass Notification Systems
| 3.2A-D | Mfg Start Up | x |  |  | x
no tie in to fa??
282300 |  | Video Survellance
| 3.3A | Mfg start up | x |  |  | x
| 3.3C | Pretest | x |  |  | x
| E | Operational Test | x |  |  | x
283111 |  | Digital Addressable Fire Alarm System
| 3.2A | Nfpa72 | x |  |  | x
202323 |  | Reuse Stockpile Structural Fill
| xxx | Test Stockpile each 2K-Y |  |  | x
406170 | SP 4.06 | HMA S-1
|  | Cores |  |  | x
406172 | SP4.06 | HMA S.375
|  | Cores |  |  | x
1301080 |  | 4", 10", 12", Hydrant Assem DI Water Main and Hydrant Assem
1301083 |  | Pressure test | x |  |  | x
1301084 |  | Sterilization | x |  |  | x
1303204 |  | Potability |  | x |  | x
Project 0118-167 Rocky Hill Repair Facility Testing Inspection Checklist (page 16 of 16)
CSI/Item # | Sub Section | Description Of Inspection/ Test | Test/ Insp Done By |  |  | Report Req
|  |  | GC | ITA | DOT
1400075 |  | 4", 6", 8", 10" PVC Force Main Sanitary Sewer
1400101 |  | Ruff in and video | x |  |  | x
1400102 |  | Pressure test | x |  |  | x
1400103 |  | Cleaning | x |  |  | x
1400185 |  | 1 1/4" HDPEP
|  | Rough in | x
|  | Final | x
|  | Pressure | x |  |  | x
|  | Clean | x |  |  | x
1403044 |  | Sanitary Pump Station
|  | Leak test | x |  |  | x
|  | Operational test | x |  |  | x
|  | Controls test | x |  |  | x
|  | Mfg start up | x |  |  | x
1404105 |  | Pump Station Sanitary Sewer
|  | Leak test | x |  |  | x
|  | Operational test | x |  |  | x
|  | Controls test | x |  |  | x
|  | Mfg start up | x |  |  | x
Miscelaneous Notes
1 | Numerous Items testing do not require cetrification in their section but my be covered by the Commisioning Spec
2
3