## key dates
PROJECT NO. | 131-205
FED AID PROJ. NO. | XXXXX
PROJECT TITLE | Southington Maintenance Facility Renovation
CITY/TOWN | Southington
PROJECT ENGINEER'S NAME | Michael Strong
FINAL DESIGN PLANS (FDP) | 2016-07-20 | No. of Days | No. of Weeks
DESIGN COMPLETION DATE (DCD) | 2016-08-31 | 42 | 6
DATE OF ADVERTISEMENT (ADV) | 2016-09-28 | 28 | 4
DATE OF LETTING | 2016-10-26 | 28 | 4
DATE OF AWARD | 2016-12-23 | 58 | 8.2857
START OF CONSTRUCTION | 2017-02-06 | 45 | 6.4286
PERMIT TIME RESTRICTIONS | N/A | N/A | #VALUE!
UTILITY WORK YES / NO | NO |  | 0
OPERATION | QUANTITY | RATE OF PRODUCTION (Amount per week) | No. of Weeks
MOBILIZATION (INCLUDING INITIAL CONTRACTOR SUBMITTALS) |  | 1 | 5
ESTABLISH PRIMARY TEMPORARY FACILITIES |  | 1 | 16
INITIAL PHASE BUILDING WORK |  | 1 | 16
INITIAL PHASE SITE WORK |  | 1 | 16
DEPARTMENT VACATES EXISTING FACILITIES |  | 1 | 1
ESTABLISH SECONDARY TEMPORARY FACILITIES |  | 1 | 12
SUMMER PHASE BUILDING WORK |  | 1 | 16
SUMMER PHASE SITE WORK |  | 1 | 16
WINTER PHASE BUILDING WORK |  | 1 | 23
WINTER PHASE SITE WORK |  | 1 | 23
FINAL PHASE BUILDING WORK |  | 1 | 13
FINAL PHASE SITE WORK |  | 1 | 13
SEMI-FINAL INSPECTION AND PUNCH-LISTS |  | 1 | 2
DEPARTMENT VACATES TEMPORARY FACILITIES |  | 1 | 1
DEMOBILIZE TEMPORARY FACILITIES & RESTORE SITE |  | 1 | 1
CLOSEOUT DOCUMENTS |  | 1 | 1
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
|  | 1 | 0
Note on B12: Please indicate the starting date of the restriction If none, say "N/A"
Note on C12: Please indicate the end date of the restriction If none, say "N/A"

## calendar 2yr
PLEASE READ FIRST:
Enter "X" to mark calendar weeks
Red Row Color = Number of weeks entered (or X's) does not match the operation quantity calculated in Column B
Weeks in Winter Shutdown (December 1st to March 31st)
| STATE OF CONNECTICUT | [26 empty] | FOR INFORMATION ONLY | [68 empty] | CALENDAR WEEKS
| DEPARTMENT OF TRANSPORTATION | [29 empty] | DATE: |  |  | June 28, 2016
| CHART FOR DETERMINING NUMBER OF CONTRACT DAYS | [61 empty] | PREPARED BY (DESIGN UNIT NAME): | Facilities Design | [17 empty] | DATE: | 06/28/16 | [13 empty] | WINTER SHUTDOWN (DEC. 1 to Mar. 31)
| FEDERAL AID PROJECT NO. | [16 empty] | TOWN |  |  |  | Southington | [14 empty] | PROJ. NO. | 131-205 | [24 empty] | REVIEWED BY (DISTRICT CONSTRUCTION): | PROJECT ENGINEER | [17 empty] | DATE:
Southington Maintenance Facility Renovation
| Construction Season |  | 2017-02-06 | [46 empty] | 2018-01-01 | [52 empty] | 2019-01-07
WORK BEGINNING DATE (STARTING MONDAYS) | [109 empty] | WEEKS ENTERED | time axis 2017-02-06 to 2019-02-18
OPERATION | QUANTITY |  | 2017-02-06: NOTICE TO PROCEED
DCD | 2016-08-31
DATE OF ADV (Wed) | 2016-09-28
DATE OF LETTING (Wed) | 2016-10-26
DATE OF AWARD (Fri) | 2016-12-23
START OF CONSTRUCTION | 2017-02-06
PERMIT RESTRICTIONS |  | N/A to N/A | [107 empty] | 0
UTILITY WORK |  | 0 | [107 empty] | 0
MOBILIZATION (INCLUDING INITIAL CONTRACTOR SUBMITTALS) |  | 5 | [107 empty] | 5 | bar: 2017-02-06 to 2017-03-06
ESTABLISH PRIMARY TEMPORARY FACILITIES |  | 16 | [107 empty] | 16 | bar: 2017-03-13 to 2017-06-26
INITIAL PHASE BUILDING WORK |  | 16 | [107 empty] | 16 | bar: 2017-03-13 to 2017-06-26
INITIAL PHASE SITE WORK |  | 16 | [107 empty] | 16 | bar: 2017-03-13 to 2017-06-26
DEPARTMENT VACATES EXISTING FACILITIES |  | 1 | [107 empty] | 1 | bar: 2017-07-03
ESTABLISH SECONDARY TEMPORARY FACILITIES |  | 12 | [107 empty] | 12 | bar: 2017-07-10 to 2017-09-25
SUMMER PHASE BUILDING WORK |  | 16 | [107 empty] | 16 | bar: 2017-07-10 to 2017-10-23
SUMMER PHASE SITE WORK |  | 16 | [107 empty] | 16 | bar: 2017-07-10 to 2017-10-23
WINTER PHASE BUILDING WORK |  | 23 | [107 empty] | 23 | bar: 2017-10-30 to 2018-04-02
WINTER PHASE SITE WORK |  | 23 | [107 empty] | 23 | bar: 2017-10-30 to 2018-04-02
FINAL PHASE BUILDING WORK |  | 13 | [107 empty] | 13 | bar: 2018-04-09 to 2018-07-02
FINAL PHASE SITE WORK |  | 13 | [107 empty] | 13 | bar: 2018-04-09 to 2018-07-02
SEMI-FINAL INSPECTION AND PUNCH-LISTS |  | 2 | [107 empty] | 2 | bar: 2018-07-09 to 2018-07-16
DEPARTMENT VACATES TEMPORARY FACILITIES |  | 1 | [107 empty] | 1 | bar: 2018-07-23
DEMOBILIZE TEMPORARY FACILITIES & RESTORE SITE |  | 1 | [107 empty] | 1 | bar: 2018-07-30
CLOSEOUT DOCUMENTS |  | 1 | [107 empty] | 1 | bar: 2018-07-30
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
0 |  | 0 | [107 empty] | 0
WEEK OF (STARTING MONDAYS) | time axis 2017-02-06 to 2019-02-18
Printed on: | 2016-06-28 08:53 |  | 2017-05-15: CALENDAR DAYS ALLOWED =; 2017-09-11: 546
OPERATIONS DURING WEEK: |  |  | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## calendar 3yr
PLEASE READ FIRST:
Enter "X" to mark calendar weeks
Red Row Color = Number of weeks entered (or X's) does not match the operation quantity calculated in Column B
Weeks in Winter Shutdown (December 1st to March 31st)
| STATE OF CONNECTICUT | [26 empty] | FOR INFORMATION ONLY | [114 empty] | CALENDAR WEEKS
| DEPARTMENT OF TRANSPORTATION | [29 empty] | DATE: |  |  | SAMPLE
| CHART FOR DETERMINING NUMBER OF CONTRACT DAYS | [61 empty] | PREPARED BY (DESIGN UNIT NAME): | PROJECT ENGINEER | [17 empty] | DATE: | [60 empty] | WINTER SHUTDOWN (DEC. 1 to Mar. 31)
| FEDERAL AID PROJECT NO. | [8 empty] | XXXXX | [7 empty] | TOWN |  |  |  | Southington | [14 empty] | PROJ. NO. | 131-205 | [24 empty] | REVIEWED BY (DISTRICT CONSTRUCTION): | PROJECT ENGINEER | [17 empty] | DATE:
Southington Maintenance Facility Renovation
| Construction Season |  | 2017-02-06 | [46 empty] | 2018-01-01 | [52 empty] | 2019-01-07 | [51 empty] | 2020-01-06
WORK BEGINNING DATE (STARTING MONDAYS) | [160 empty] | WEEKS ENTERED | time axis 2017-02-06 to 2020-02-10
OPERATION | QUANTITY |  | 2017-02-06: NOTICE TO PROCEED
DCD | 2016-08-31
DATE OF ADV (Wed) | 2016-09-28
DATE OF LETTING (Wed) | 2016-10-26
DATE OF AWARD (Fri) | 2016-12-23
START OF CONSTRUCTION | 2017-02-06
PERMIT RESTRICTIONS |  | N/A to N/A | [158 empty] | 0
UTILITY WORK |  | 0 | [158 empty] | 26 | bar: 2017-04-24 to 2017-10-16
MOBILIZATION (INCLUDING INITIAL CONTRACTOR SUBMITTALS) |  | 5 | [158 empty] | 1 | bar: 2017-04-10
ESTABLISH PRIMARY TEMPORARY FACILITIES |  | 16 | [158 empty] | 1 | bar: 2017-04-17
#REF! |  | #REF! | [158 empty] | 8 | bar: 2017-07-24 to 2017-09-11
#REF! |  | #REF! | [158 empty] | 3 | bar: 2017-09-18; 2017-10-09; 2017-10-23
#REF! |  | #REF! | [158 empty] | 6 | bar: 2017-09-18 to 2017-10-23
#REF! |  | #REF! | [158 empty] | 2 | bar: 2017-10-30 to 2017-11-06
#REF! |  | #REF! | [158 empty] | 2 | bar: 2017-11-13; 2018-04-09
#REF! |  | #REF! | [158 empty] | 3 | bar: 2017-11-20 to 2017-11-27; 2018-04-16
#REF! |  | #REF! | [158 empty] | 1 | bar: 2018-07-16
#REF! |  | #REF! | [158 empty] | 1 | bar: 2018-07-23
#REF! |  | #REF! | [158 empty] | 2 | bar: 2017-11-27; 2018-07-23
#REF! |  | #REF! | [158 empty] | 14 | bar: 2018-04-23 to 2018-07-23
#REF! |  | #REF! | [158 empty] | 4 | bar: 2017-11-27 to 2017-12-04; 2018-05-21 to 2018-05-28
#REF! |  | #REF! | [158 empty] | 1 | bar: 2017-12-04
#REF! |  | #REF! | [158 empty] | 1 | bar: 2018-07-30
#REF! |  | #REF! | [158 empty] | 2 | bar: 2018-08-06 to 2018-08-13
#REF! |  | #REF! | [158 empty] | 1 | bar: 2018-08-20
INITIAL PHASE BUILDING WORK |  | 16 | [158 empty] | 0
INITIAL PHASE SITE WORK |  | 16 | [158 empty] | 0
DEPARTMENT VACATES EXISTING FACILITIES |  | 1 | [158 empty] | 0
ESTABLISH SECONDARY TEMPORARY FACILITIES |  | 12 | [158 empty] | 0
SUMMER PHASE BUILDING WORK |  | 16 | [158 empty] | 0
SUMMER PHASE SITE WORK |  | 16 | [158 empty] | 0
WINTER PHASE BUILDING WORK |  | 23 | [158 empty] | 0
WINTER PHASE SITE WORK |  | 23 | [158 empty] | 0
FINAL PHASE BUILDING WORK |  | 13 | [158 empty] | 0
FINAL PHASE SITE WORK |  | 13 | [158 empty] | 0
SEMI-FINAL INSPECTION AND PUNCH-LISTS |  | 2 | [158 empty] | 0
DEPARTMENT VACATES TEMPORARY FACILITIES |  | 1 | [158 empty] | 0
DEMOBILIZE TEMPORARY FACILITIES & RESTORE SITE |  | 1 | [158 empty] | 0
CLOSEOUT DOCUMENTS |  | 1 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
0 |  | 0 | [158 empty] | 0
WEEK OF (STARTING MONDAYS) | time axis 2017-02-06 to 2020-02-10
Printed on: | 2016-06-28 08:53 |  | 2017-05-15: CALENDAR DAYS ALLOWED =; 2017-09-11: 385
OPERATIONS DURING WEEK: |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0